## Sheet1
Questions? Contact Nick Szubiak nick@nsistrategies.com (808) 895.7679 www.nsistrategies.com
NSI Strategies Population Health Management Strategic Workplan Tool
Work Plan Deliverables | Training Scenario Example | Your Health Center info
Strategic Plan | Decrease A1C scores by increasing access to BH supports
Convene Core Implementation Team | PCP, BH, Nursing, IT, Finance
What is our Quality Metric/Key Performance Indicator Definition | All patients with an A1C score greater than 7% and receive a BH
Metric Numerator | Pts with A1C score greater than 7% that receive BH intervention (90832,90834,90837)
Metric Denominator | Pts with A1C score greater than 7%
Metric Exclusions | Under 18
Report Period | 1x per month for 12 months
Data Registry | Utilize EHR/Excel
Performance Target Outcomes | 1. Increase population to Behavioral Health support 2. Decrease A1C scores
Map the Care Pathway | Completed
Policy and Procedure | Submitted to P&P Committee
Review Evidenced Based Interventions | In Process - BH training on Behavioral Activation Planning
Clinical and Admin Protocols | MD to order standing order
Pilot the Care Pathway | In process
CQI - Evaluate efficiency and effectiveness of the care pathway | Measure submitted to QI Team
Update and Adjust Admin and Clinical Protocols as needed (PDSA) | Next meeting review data
Performance Indicator/Quality Metrics for Ongoing Monitoring | N/A
Date to Roll-out Expansion | Champion Team 1-2 Months, Site A 2-4 months; Health Center Wide 5-6 months